## Slide 1: Examining Arlington County's Board Structure and Performance June 2026 Update
Susan Cunningham & JD Spain Sr.
06/17/2026

## Slide 2
Timeline Update
Quarter | Milestone | Target Dates/Delivery
Launch | Publish Interest Form, Commitment of Initial Efforts to Examine the Board's Structure | December 2025
Q1 | Begin Resident Community Satisfaction Survey work | February 2026
Q1 | Identify financial resources and establish procurement process to support external research | March 2026
Q1 | County Attorney Begins legal research, School and Electoral Boards engaged, routine Comms begins | March 2026
Q2 | Begin search for External Research Partners, Issue Scope of Work | April 2026
Q2 | PUBLIC UPDATE re REVISION TO TIMELINE | June 2026
Q3 | Public Report on Resident Community Satisfaction Survey findings | June 2026
Q3 | County Attorney's Public Report of Legal Research | July 2026
Q3 | Selection of External Research Partner, research work begins | July 2026 (Anticipated)
Q3 | Initial Report from External Research Partner | October 30th, 2026
Q4 | Final Report from External Research Partner | November 30th, 2026
Q4 | Board Update | December 2026
UPDATE: The Board will still provide a public update in July, and its public report on next steps will be December 2026.
The research partner procurement and delivery timeline are revised to encourage more respondents. All other previously identified tasks remain on schedule.